## Input
Program Configuration | [6 empty] | Sprint Metrics & Planning | [6 empty] | Show Forecast
| Team Name | # of Developers |  | Observed Holidays | Date | Capacity (%) |  | Sprint Ending | Sprint Number | Estimated Effort | Completed Work | Known Effort | Scheduled Work
| Team 1 | 8 | Secular | New Year | 2025-01-01 | 25% |  | 2024-10-25 | 24.42 | 500 | 10 | 25 | 2 | N/A
| Team 2 | 0 |  | Martin Luther King, Jr. Day | 2025-01-16 | 95% |  | 2024-11-08 | 24.44 | 500 | 10 | 77 | 5 | No
| Team 3 | 0 |  | President's Day | 2025-02-14 | 95% |  | 2024-11-22 | 24.46 | 500 | 15 | 87 | 15 | No
| Team 4 | 0 |  | Spring Festival (Asia) | 2025-02-08 | 50% |  | 2024-12-06 | 24.48 | 500 | 15 | 145 | 15 | No
| Team 5 | 0 |  | Spring Break Start | 2025-03-27 | 80% |  | 2024-12-20 | 24.50 | 437 | 30 | 168 | 30 | No
| Team 6 | 0 |  | Memorial Day | 2025-05-31 | 95% |  | 2025-01-03 | 25.00 | 437 | 21 | 241 | 21 | No
| Team 7 | 0 |  | Independence Day | 2025-07-04 | 80% |  | 2025-01-17 | 25.02 | 437 | 38 | 341 | 36 | No
|  | Points / Sprint |  | Labor Day | 2025-09-04 | 80% |  | 2025-01-31 | 25.04 | 437 | 42 | 362 | 35 | No
| Developer Velocity | 5 |  | Thanksgiving | 2025-11-26 | 50% |  | 2025-02-14 | 25.06 | 445 | 40 | 395 | 40 | No
|  |  | Religious | Ash Wednesday | 2025-02-04 | 95% |  | 2025-02-28 | 25.08 | 445 | 40 | 415 | 42 | Yes
| Development Start | 2024-10-14 |  | Good Friday | 2025-04-05 | 95% |  | 2025-03-14 | 25.10 | 445 | 40 |  | 40 | Yes
| Development End | 2025-05-16 |  | Eid | 2025-05-17 | 95% |  | 2025-03-28 | 25.12 | 445 |  |  | 50 | Yes
| Weeks / Sprint | 2 |  | Yom Kippur | 2025-09-05 | 95% |  | 2025-04-11 | 25.14 | 445 |  |  | 55 | Yes
|  |  |  | Rosh Hashanah | 2025-09-30 | 95% |  | 2025-04-25 | 25.16 | 445 |  |  | 42 | Yes
|  |  |  | Christmas | 2024-12-25 | 75% |  | 2025-05-09 | 25.18 | 445 |  |  |  | No
|  |  |  | Maha Shivaratri | 2025-03-08 | 75% |  | 2025-05-23 | 25.20 | 445 |  |  |  | No
|  |  |  | Ramadan Begins | 2025-03-10 | 85% |  | 2025-06-06 | 25.22 | 445 |  |  |  | No
|  |  |  | Shri Ramakrishna Jayanti | 2025-03-15 | 95% |  | 2025-06-20 | 25.24 | 445 |  |  |  | No
|  |  |  | Ramadan Ends | 2025-04-09 | 85% |  | 2025-07-04 | 25.26 | 445 |  |  |  | No
|  |  |  | Eid al-Fitr | 2025-04-10 | 85% |  | 2025-07-18 | 25.28 | 445 |  |  |  | No
|  |  |  | Passover Begins | 2025-04-22 | 95% |  | 2025-08-01 | 25.30 | 445 |  |  |  | No
|  |  |  | Passover Ends | 2025-04-30 | 95% |  | 2025-08-15 | 25.32 | 445 |  |  |  | No
|  |  |  | Shavuot | 2025-06-11 | 95% |  | 2025-08-29 | 25.34 | 445 |  |  |  | No
|  |  |  | Eid-ul-Adha | 2025-06-16 | 85% |  | 2025-09-12 | 25.36 | 445 |  |  |  | No
|  |  |  | Ashura | 2025-07-16 | 85% |  | 2025-09-26 | 25.38 | 445 |  |  |  | No
|  |  |  | Krishna Janmashtami | 2025-08-26 | 75% |  | 2025-10-10 | 25.40 | 445 |  |  |  | No
|  |  |  | Mawlid-al-Nabi | 2025-09-15 | 85% |  | 2025-10-24 | 25.42 | 445 |  |  |  | No
|  |  |  | Birth of Guru Nanak | 2025-11-15 | 95% |  | 2025-11-07 | 25.44 | 445 |  |  |  | No
| Projected Velocity Template by Michael Rodighiero |  |  | LinkedIn | Medium
v. 10.24
Formulas:
Sprint Ending = IF(WEEKNUM(L48+(7*Input!$D16))=1,[Sprint Ending, row above]+28,[Sprint Ending, row above]+(7*Input!$D16))
Sprint Number = IF(LEN(CONCATENATE(RIGHT(YEAR([Sprint Ending]),2),".",WEEKNUM([Sprint Ending])-1))=5,CONCATENATE(RIGHT(YEAR([Sprint Ending]),2),".",WEEKNUM([Sprint Ending])-1),CONCATENATE(RIGHT(YEAR([Sprint Ending]),2),".0",WEEKNUM([Sprint Ending])-1))

## BE (hidden)
Total Developers | 8
Gross Program Velocity | 40
Sprints | 15
Capaity Adjustments |  |  | Chart Data
Observance | Sprint | Adjusted Capacity | Sprint Number | Sprint End | Projectected Capacity | Projected Velocity | Planned Effort | Known Effort | Estimated Effort | Progress | Forecast
New Year | 24.52 | 10 | 24.42 | 2024-10-25 | 40 | 40 | 2 | 25 | 500 | 10 | N/A
Martin Luther King, Jr. Day | 25.02 | 38 | 24.44 | 2024-11-08 | 40 | 80 | 5 | 77 | 500 | 20 | #N/A
President's Day | 25.06 | 38 | 24.46 | 2024-11-22 | 40 | 120 | 15 | 87 | 500 | 35 | #N/A
Spring Festival (Asia) | 25.06 | 20 | 24.48 | 2024-12-06 | 40 | 160 | 15 | 145 | 500 | 50 | #N/A
Spring Break Start | 25.12 | 32 | 24.50 | 2024-12-20 | 40 | 200 | 30 | 168 | 437 | 80 | #N/A
Memorial Day | 25.22 | 38 | 25.02 | 2025-01-17 | 38 | 238 | 36 | 341 | 437 | 118 | #N/A
Independence Day | 25.26 | 32 | 25.04 | 2025-01-31 | 38 | 276 | 35 | 362 | 437 | 160 | #N/A
Labor Day | 25.36 | 32 | 25.06 | 2025-02-14 | 20 | 296 | 40 | 395 | 445 | 200 | #N/A
Thanksgiving | 25.48 | 20 | 25.08 | 2025-02-28 | 20 | 316 | 42 | 415 | 445 | 240 | #N/A
Ash Wednesday | 25.06 | 38 | 25.10 | 2025-03-14 | 20 | 336 | 40 | #N/A | 445 | 280 | 280
Good Friday | 25.14 | 38 | 25.12 | 2025-03-28 | 32 | 368 | 50 | #N/A | 445 | #N/A | 330
Eid | 25.20 | 38 | 25.14 | 2025-04-11 | 32 | 400 | 55 | #N/A | 445 | #N/A | 385
Yom Kippur | 25.36 | 38 | 25.16 | 2025-04-25 | 32 | 432 | 42 | #N/A | 445 | #N/A | 427
Rosh Hashanah | 25.40 | 38 | 25.18 | 2025-05-09 | 32 | 464 | #N/A | #N/A | 445 | #N/A | #N/A
Christmas | 24.52 | 30 | 25.20 | 2025-05-23 | 32 | 496 | #N/A | #N/A | 445 | #N/A | #N/A
Maha Shivaratri | 25.10 | 30 | 25.22 | 2025-06-06 | 38 | 534 | #N/A | #N/A | 445 | #N/A | #N/A
Ramadan Begins | 25.1 | 34 | 25.24 | 2025-06-20 | 38 | 572 | #N/A | #N/A | 445 | #N/A | #N/A
Shri Ramakrishna Jayanti | 25.1 | 38 | 25.26 | 2025-07-04 | 32 | 604 | #N/A | #N/A | 445 | #N/A | #N/A
Ramadan Ends | 25.14 | 34 | 25.28 | 2025-07-18 | 32 | 636 | #N/A | #N/A | 445 | #N/A | #N/A
Eid al-Fitr | 25.14 | 34 | 25.30 | 2025-08-01 | 32 | 668 | #N/A | #N/A | 445 | #N/A | #N/A
Passover Begins | 25.16 | 38 | 25.32 | 2025-08-15 | 32 | 700 | #N/A | #N/A | 445 | #N/A | #N/A
Passover Ends | 25.18 | 38 | 25.34 | 2025-08-29 | 32 | 732 | #N/A | #N/A | 445 | #N/A | #N/A
Shavuot | 25.24 | 38 | 25.36 | 2025-09-12 | 32 | 764 | #N/A | #N/A | 445 | #N/A | #N/A
Eid-ul-Adha | 25.24 | 34 | 25.38 | 2025-09-26 | 38 | 802 | #N/A | #N/A | 445 | #N/A | #N/A
Ashura | 25.28 | 34 | 25.40 | 2025-10-10 | 38 | 840 | #N/A | #N/A | 445 | #N/A | #N/A
Krishna Janmashtami | 25.34 | 30 | 25.42 | 2025-10-24 | 30 | 870 | #N/A | #N/A | 445 | #N/A | #N/A
Mawlid-al-Nabi | 25.38 | 34 | 25.44 | 2025-11-07 | 30 | 900 | #N/A | #N/A | 445 | #N/A | #N/A
Birth of Guru Nanak | 25.46 | 38 | 25.46 | 2025-11-21 | 30 | 930 | #N/A | #N/A | #N/A | #N/A | #N/A
Formulas:
Sprint Number = TRIM(IF(LEN(CONCATENATE(RIGHT(YEAR([Sprint End]),2),".",WEEKNUM([Sprint End])-1))=5,CONCATENATE(RIGHT(YEAR([Sprint End]),2),".",WEEKNUM([Sprint End])-1),CONCATENATE(RIGHT(YEAR([Sprint End]),2),".0",WEEKNUM([Sprint End])-1)))
Sprint End = IF(WEEKNUM([Sprint End, row above]+(7*Input!$D16))=1,[Sprint End, row above]+28,[Sprint End, row above]+(7*Input!$D16))